# Earned Value Analysis (EVA)

Our project involves the development of the ZeroWastee platform — a real-time food donation and delivery coordination system that connects donors, volunteers, and NGOs to reduce food waste in urban areas. The project is divided into 3 major phases (Planning, Development, and Testing & Deployment) with a total of 15 planned work tasks. The total estimated project effort is 900 person-days.

As of now, 5 tasks have been completed, while according to the project schedule, 6 tasks were planned to be completed at this stage. The following scheduling data (in person-days) has been used to perform the Earned Value Analysis to measure project progress and performance.

## Project Details:

- Total Planned Tasks: 15
- Total Effort Estimated: 900 person-days
- Tasks Completed: 5
- Tasks Scheduled to be Completed: 6

## Available Scheduling Data (in person-days):

- BCWS (Budgeted Cost of Work Scheduled): 360 person-days
- BCWP (Budgeted Cost of Work Performed): 300 person-days
- ACWP (Actual Cost of Work Performed): 325 person-days

## EVA Calculations

Schedule Performance Index (SPI)

SPI = BCWP / BCWS = 300 / 360 = 0.8333 = 83.33%

Schedule Variance (SV)

SV = BCWP - BCWS = 300 - 360 = -60 person-days

Cost Performance Index (CPI)

CPI = BCWP / ACWP = 300 / 325 = 0.923 = 92.30%

Cost Variance (CV)

CV = BCWP - ACWP = 300 - 325 = -25 person-days

Percentage Schedule Completion

% Schedule Completion = BCWS / BAC = 360 / 900 = 40.00%

Percentage Work Completed

% Work Completed = BCWP / BAC = 300 / 900 = 33.33%

## Task Summary Table

| Task | Planned Effort (hrs) | Actual Effort (hrs) |
| --- | --- | --- |
| User Registration Module | 70 | 74 |
| Food Donation Posting | 55 | 58 |
| Real-Time Tracking Integration | 65 | 69 |
| Smart Matching Algorithm | 60 | 63 |
| Volunteer Dashboard | 50 | 61 |
| NGO Verification System | 60 | — |

## Analysis Summary

• Schedule Performance: The project is behind schedule (SPI = 83.33%)
• Cost Performance: The project is slightly over budget (CPI = 92.30%)
• Schedule Variance: 60 person-days behind planned schedule
• Cost Variance: 25 person-days over planned budget
• Overall Progress: 33.33% work completed vs 40.00% scheduled completion

Interpretation:
The current analysis indicates that the ZeroWastee project is slightly lagging behind its planned progress and has incurred minor cost overruns due to increased testing and integration time for real-time tracking and volunteer dashboard modules. Timely corrective measures — such as improved resource allocation, weekly progress reviews, and incremental testing — can help bring the project back on track.